PROJECT INTENT

Company: M/S DIPTY LAL JUDGE MAL PVT. LTD.

Indian Standard: IS 302: Part 2: Sec 9

| S.No. | Activity | Status | Remarks | Planned | Actual |
| --- | --- | --- | --- | --- | --- |
| 1 | Registration & Business Profile | Done | Registration was completed over manak online portal | Done | Done |
| 2 | TRF Generate | Done | TRF Was generated successfully | Done | Done |
| 3 | Pre Audit & Document collection | Done | - | - | - |
| 3 | Test Report | Pending | Test Report w | 10-August-2026 | - |
| 4 | Application Submission | Pending | We will submit the application Once we get the test report and all the docs | 10-August-2026 | - |
| 5 | BIS Officer Visit | Pending | BIS auditor will visit within 17 days after submission of the application | 18-August-2026 | - |
| 6 | Sample Sealing | Pending | On the same day of the inspection | 18-August-2026 | - |
| 7 | CM/L Number or License Granted | Pending | License will be granted within 30 days from the date of submission of the application | 25-August-2026 | - |

-